# Google.org Grant Proposal

INTRODUCTION: Thank you for applying for a grant with Google.org. This template includes 4 Sections and should take 1-2 hrs to complete. Please no more than 4-5 pages total.  Google.org and, where applicable, a Google donor advised fund partner (Tides Foundation or Give2Asia), will have access to the personally identifiable information (PII) you provide. PII will be used solely to evaluate your organization’s grant proposal and to contact you should additional information be required. The information you provide will be used in accordance with Google's Privacy Policy and, where applicable, a Google donor advised fund partner’s privacy policy (see Tides’ Privacy Policy and Give2Asia Privacy Policy). After submitting this form, if you would like your information deleted, please email dotorg-stratops@google.com and, where applicable, Google’s donor advised fund partner (for Tides, contact ­­­­­­­­­­­­­­­­­­info@tides.org or for GDPR specific requests contact GDPR@tides.org; for Give2Asia contact info@give2asia.org ). Please do not provide confidential or proprietary information in this form.

Section A: Organization Information

| Organization Information |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Organization name: | Università Campus Bio-Medico di Roma |  |  |  |  |
| Organization type: | - U.S. 501(c)(3) public charity - Social enterprise |  | - Non-U.S. charitable nonprofit - Other: Private University |  |  |
| Fiscal Year End Date (e.g. Dec 31st or June 30th): December 31st |  |  | Year Founded: 1992 |  |  |
| Grantee Mission Statement: | To promote integrated teaching, research, and healthcare structures, pursuing as the main end of all its activities the good of the human person. |  |  |  |  |

Section B: Grant Information

| Project Description |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Grant amount (“Grant Funds”): |  |  | €450,000 |  |  |
| Payment Structure: |  |  | - Single Payment - Milestones |  |  |
| Grant Announcement Date: |  |  | October 17, 2023 |  |  |
| Charitable class supported by the Project (“End Beneficiaries”): |  |  | The Project will support the following End Beneficiaries: - Underserved workers and entrepreneurs working in small and medium sized enterprises (SMEs), defined as less than 25 employees, and micro-enterprises across Italy who do not have equal access or technical resources and financial resources to take action on cyberthreats to their businesses. Grantee will particularly focus on End Beneficiaries who are based in underserved areas, including southern regions of Italy, to help establish professional longevity in cyber security, and increase cyber security education to communities with little to no existing access. - Underserved workers and entrepreneurs working in NGOs and non profits in Italy, who are vulnerable to cyber attacks but lack financial and technical resources to take action on cyberthreats to their organizations |  |  |
| Project supported with Grant Funds (“Project”): |  |  | Università Campus Bio-Medico di Roma will use Grant Funds to enhance and develop their existing Minimum Viable Product, which can associate in real time the degree of hypothetical attacks on operational technology in Italian SMEs using AI-driven approach, such as Time-Varying Dynamic Bayesian Networks, and provide effective countermeasures using Analytic Hierarchy Process decision making techniques. The AI tool will gather open source, unstructured data from the internet on vulnerabilities. During an attack, users can feed information and data on the network and firewall, and the tool will provide real time suggestions to address the attack and mitigate damages. Università Campus Bio-Medico di Roma will partner with Politecnico di Milano to train the existing Minimum Viable Product to recognise and counter attacks on Operational Technologies, and plug this technology into the base platform developed by Politecnico di Milano, which is a AI and web platform that disseminates actionable cybersecurity recommendations to End Beneficiaries. Additionally, Grantee will partner with ecosystem partners to ensure widespread promotion and adoption amongst End Beneficiaries. With Grant Funding, Università Campus Bio-Medico di Roma will; - Hire additional researchers to design and implement the engine of the operational platform, and design and implement the user interface and platform database - Collect data on cybersecurity vulnerabilities from an Operational Technology perspective, including data from hardware and software that monitors and/or controls manufacturing equipment and processes. - Build recommendation algorithm for security reaction in the case of cyber attack - Train the existing MVP to recognise and counteract cyber attacks on Operational Technology. This includes a component for identifying attacks by analyzing web events and data provided by end users; an expert system that suggests solutions to cyber attacks (for example, actions such as system shutdowns and alerts) to aid detection of attacks that exploit Operational Technologies - Define the technical requirements to integrate the tool into Politecnico di Milano’s base platform, and work closely to align on designs and requirements - Plug tool into Politecnico platform and test, ensure the developed content is open-sourced and available to all. The impact of this work will be: - To democratize access to cybersecurity intelligence, making it easily and specifically available to communities traditionally marginalized, including those in underserved regions of Italy including Southern regions - A 10% to 20% adoption rate among Italy's 3.6 million SMEs (360,000 to 720,000 SMEs) - To contribute to a 30% reduction in cyber attacks on Italian SMEs and a 20% increase in employee awareness of such cyber threats. |  |  |
| Budget |  |  |  |  |  |
| Category | Expense |  |  |  | Amount |
| Direct Costs | Hiring a junior researcher to design and implement the engine of the Operational Technology platform over 3 years |  |  |  | €170,000 |
|  | Hiring one junior researcher to design and implement user interface and platform database over 2 years |  |  |  | €75,000 |
|  | Hiring one staff member to support roll out and dissemination activities over 2 years |  |  |  | € 45,000 |
|  | Investments in existing staff to support the development of the platform, managing the scientific and technological issues and to support cooperation with Unindustria, public institutions and SMEs |  |  |  | €50,000 |
|  | Publishing results to 3 research journals |  |  |  | € 10,000 |
|  | Conference costs to publicize tool |  |  |  | € 10,000 |
|  | Joint project meetings with Politecnico di Milano |  |  |  | € 5,000 |
|  | User Feedback Sessions: Interactive discussions with SMEs currently using or interested in the tool, aimed at gathering crucial feedback for further development and improvement. |  |  |  | € 20,000 |
|  | Participation events with stakeholders - Industry Collaboration: Engagements with ecosystem partners to tap into their networks and influence to encourage tool adoption. |  |  |  | € 10,000 |
|  | Meetings with stakeholders, authorities & SMEs(launch and training event) - Cybersecurity Workshops - Webinars and Online Tutorials - Employee Awareness Programs - Launch meeting |  |  |  | € 10,000 |
| Indirect Costs | Administration & Management |  |  |  | € 45,000 |
| Total Grant Funds |  |  |  |  | €450,000 |
| - YES - NO | Grantee is providing unrestricted funding to individuals |  |  |  |  |
| - YES - NO | Grantee is providing sub grants to other organizations |  |  |  |  |
| Grant Schedule |  |  |  |  |  |
| Grantee will complete the Project activities and outcomes by the due date below. For milestone grants, payments will be made following Grantee’s successful completion of Project activities and outcomes by the due date. |  |  |  |  |  |
| Project Activities |  |  |  | Project Outcomes | Due Date |
| Execution of Grant Agreement |  |  |  | N/A |  |
| Activity 1: Hire additional technical researchers to supplement team |  |  |  | - 2 Junior Technical Researchers hired and onboarded | January 2024 - March 2024 |
| Activity 2: Conduct desk research and literature review to understand existing methodologies and AI summarisation techniques. Conduct user research to define product roadmap, user interface and non functional requirements around data security, user access and authentication |  |  |  | - Objectives of the project and scope of the technical solution are defined. - Conducted user research with 50 End Beneficiaries, with support from ecosystem partners - Literature review regarding existing methodologies and technologies completed | February 2024 - June 2024 |
| Activity 3: Perform data exploration. Create and set up a data ingestion pipeline that can combine cyber threat intelligence from various sources, including Operational Technologies vulnerabilities. |  |  |  | - Data is explored, analyzed and processed accordingly - Confirmed access to required datasets and set up infrastructure to ingest it - Refined technical plan based on data discovery results - 3 research journals published | March 2024 - October 2024 |
| Activity 4: Conduct model validation on the base technology platform from Politecnico di Milano; test the platform and iterate based on test results |  |  |  | - Academic research informed the interpretation methodology, and is submitted to international conferences and workshops - The interpretation methodology was identified and applied to the model. - Iterations to the product are integrated based on test results. | September 2024 - November 2025 |
| Activity 5: Conduct Minimum Viable Product validation and testing for the Operational Technology modular plug-in to determine scalability, integration with the base technology platform, and iterate based on test results |  |  |  | - The plug-in Minimum Viable Product is trained on existing data. - The plug-in Minimum Viable Product is scaled beyond a single network. - The Minimum Viable Product is built as a modular tool that can be plugged into the platform. | May 2025 - May 2026 |
| Activity 6: Develop a Minimum Viable Product (MVP) for the combined system (base technology platform led by Politecnico and integrating the plug-in from Bio-Medico); test to ensure quality assurance user testing with 10 SMEs selected with the support of Assolombarda and Unindustria. |  |  |  | - Minimum Viable Product is successfully integrated into the base technology platform - The Minimum Viable Product for the combined system is tested with 10 SMEs, selected by Assomolbarda and Unindustria users to gather feedback - Beta version developed, incorporating feedback from user validation sessions | May 2025 - May 2026 |
| Activity 7: Develop a maintenance plan to support and scale up the product |  |  |  | - A maintenance plan is developed in collaboration with ecosystem partners which outlines the support and scale up the product is developed. | March 2026 - November 2026 |
| Activity 8: Develop a launch strategy for tool dissemination in the SME ecosystem in Italy, Including onboarding support from ecosystem partners to implement the go-to-market plan. |  |  |  | - Market analysis and business planning were conducted. - Launch strategy is developed and implemented, in collaboration with ecosystem partners, and product is open-sourced and made available to users for free | January 2026 - August 2026 |
| Activity 9: Deliver capacity building and training workshops targeted to End Beneficiaries in underserved communities. - Cybersecurity training workshops to sessions, in partnership with educational institutions and industry organizations, to educate SME owners and IT staff about cybersecurity and the tool. - Webinars and Online Tutorials to educate users on how to effectively use the tool and maintain good cybersecurity practices. - Employee Awareness Programs: Specialized training sessions directly with SMEs to educate employees on identifying common cyber threats and how the tool can help |  |  |  | - Six training events conducted, with 100 End Beneficiaries in Lombardia, Lazio and Southern Italian Regions | April 2026 - December 2026 |
| Activity 10: Organize four in person launch events and undergo marketing to promote and distribute the platform and increase awareness amongst End Beneficiaries. This includes engaging with and National Cybersecurity Authority (ACN) |  |  |  | - 4 launch events, (Lazio, Lombardy and Southern Italian regions) held that increased awareness and adoption of the platform. | April 2024 - December 2026 |
| Impact Measurement Reporting |  |  |  |  |  |
| On an annual basis in the reporting period listed below, Grantee will measure the beneficiaries, outputs, and outcomes of the Project (“Impact Measurement”). Following Grantee’s annual completion of Impact Measurement, Grantee will complete the impact survey report(s) linked below (“Impact Survey”), due by January 31st. Grantee will provide anonymized and aggregated Impact Survey results in accordance with instructions. |  |  |  |  |  |
| Impact Survey |  |  |  |  |  |
| ¦ Impact Challenge ¦ |  |  |  |  |  |
| Project Start Date | Jan 2024 |  |  | Project End Date | Dec 2026 |
| First Report Due Date | Jan 2025 |  |  | Final Report Due Date | Jan 2027 |

Section C: Supplemental Grant Information

| Project Background |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Problem Statement [In bullets and leveraging data, what is the problem you are trying to tackle?] |  |  | Describe the problem your project is addressing in 2-3 bullets: - The digital transformation of small and medium-sized enterprises (SMEs) has enhanced productivity, and new capabilities in monitoring of machinery and equipment across various systems. Nevertheless, this heightened connectivity also brings along inherent risks related to cyber exposure. - Cybersecurity is a systemic problem, requiring costly and specialized expertise. SMEs lack the financial resources to access essential cyber security expertise, and are therefore ill equipped to understand, defend and respond to cyberthreats. - In Italy, where SMEs account for 99.9% of organizations (with 95% being micro-enterprises with fewer than 10 employees), this issue becomes particularly critical and widespread. It can impact both their competitiveness and compromise entire value chains. |  |  |  |
| Proposed Solution [What solution are you proposing and what evidence do you have that this will be successful?] |  |  | Describe your ideas in 2-3 sentences and their significance - A web application leveraging AI (Natural Language Processing and Large Language Model) to develop a pipeline for collecting cyber threat intelligence from various sources and disseminating this information free of charge to End Beneficiaries. - The web application would not only be able to identify cyber threats and vulnerabilities but also suggest actionable and tailored recommendations based on current and historical data, and field cybersecurity-related questions. - The tool would help End Beneficiaries understand cases of vulnerability exploitation and act in real-time to counter an ongoing attack or take preventative action. |  |  |  |
| Scalability [What specific model will you rely on to scale the impact of this project?] |  |  | - Model 1: Partnerships with to ensure widespread promotion and PR to End Beneficiaries |  |  |  |
| Learning [What questions do you seek to answer through this project that will help you improve your services/ inform the field?] |  |  | - How will the platform communicate information on cyber attacks and vulnerabilities in a way that is both clear and accessible to a non-technical audience? - How will the tool help SMEs build in house expertise and capability to ensure long-term cybersecurity resilience? |  |  |  |

CERTIFICATION: By submitting this form, I certify on behalf of myself and my organization that: (1) the people listed by name in this form have agreed to being contacted by Google and, where applicable, a Google Donor Advised Fund Partner (Tides Foundation or Give2Asia)  for purposes of evaluating my organization’s application for a grant; (2) all information contained in this form is true and accurate; (3) none of the information in this form is confidential or proprietary; and (4) I am an authorized representative of my organization who has the authority and permission from my organization to submit this form and the authority to legally bind the organization.